## Sheet1
Est. Hours | Description of Work
2 | Refine specification/requirements
4 | Gather and review relevant data sheets for electrical requirements
3 | Define power requirements and select voltage regulators
20 | Electrical Design / Circuit Simulation / Schematic capture
10 | PCB Layout / BOM Generation
2 | Review / Deliver / Post-delivery consultation
41 | Estimated Total
Hours | Description of Work | Date
1 | Refine specification/requirements | 2019-03-28
1 | Refine specification/requirements | 2019-04-04
2 | Gather and review data sheets | 2019-04-04
8 | Electrical Design / Sim / Schematic | 2019-04-04
2 | Electrical Design / Sim / Schematic | 2019-04-05
4 | Electrical Design / Sim / Schematic / PCB Layout | 2019-04-06
3 | Electrical Design / Sim / Schematic / PCB Layout | 2019-04-07
2 | Electrical Design / Sim / Schematic / PCB Layout | 2019-04-08
3 | Power Supply / PCB Layout | 2019-04-08
2 | Power Supply / PCB Layout | 2019-04-08
1 | CAN Chokes, Power Supply Inductors | 2019-04-11
2 | PCB Layout | 2019-04-29
3 | PCB Layout | 2019-05-01
2 | BOM | 2019-05-02
36 | Progress | 87.8%