## v1.0 Complete
Est. Hours | Description of Work
2 | Refine specification/requirements
4 | Gather and review relevant data sheets for electrical requirements
3 | Define power requirements and select voltage regulators
20 | Electrical Design / Circuit Simulation / Schematic capture
10 | PCB Layout / BOM Generation
2 | Review / Deliver / Post-delivery consultation
41 | Estimated Total
Hours | Description of Work | Date
1 | Refine specification/requirements | 2019-03-28
1 | Refine specification/requirements | 2019-04-04
2 | Gather and review data sheets | 2019-04-04
8 | Electrical Design / Sim / Schematic | 2019-04-04
2 | Electrical Design / Sim / Schematic | 2019-04-05
4 | Electrical Design / Sim / Schematic / PCB Layout | 2019-04-06
3 | Electrical Design / Sim / Schematic / PCB Layout | 2019-04-07
2 | Electrical Design / Sim / Schematic / PCB Layout | 2019-04-08
3 | Power Supply / PCB Layout | 2019-04-08
2 | Power Supply / PCB Layout | 2019-04-08
1 | CAN Chokes, Power Supply Inductors | 2019-04-11
2 | PCB Layout | 2019-04-29
3 | PCB Layout | 2019-05-01
2 | BOM | 2019-05-02
1 | PCB Mounting holes, tie-strap holes, logo | 2019-05-03
2 | BOM, Gerber Generation | 2019-05-13
1 | Review - identify errata and potential corrections. | 2019-05-27
40 | Progress | 97.56%
Project Complete: Invoice 20190601

## v1.0 20190601
Smartware Computing | INVOICE
| DATE: | 2019-06-01
David Smart 907 Sunrise Blvd | PROJECT: | Telematics Platform
Waterloo, IA 50701 | INVOICE # | 20190601
319-830-6947
Bill To: | Bill Rate $/h | 85
Hughes Fire Equipment, Inc.
c/o Sonny Ovens
910 Shelley Street
Springfield, OR 97477
541-747-0072
DESCRIPTION | HOURS | AMOUNT
Electrical and PCB Design for the Hughes Telematics Platform - Specification v1.0 | 40 | 3400
| TOTAL | 3400
Make all checks payable to Smartware Computing
If you have any questions concerning this invoice, Contact David Smart.
THANK YOU FOR YOUR BUSINESS!

## v1.1 Complete
Est. Hours | Description of Work
2 | Correct v1.0 issues, enhance for RTC battery
2 | Estimated Total
Hours | Description of Work | Date
0 | Correction to v1.0; Revision to Power Supply, Keep-Alive | 2019-10-12
1 | Add Battery Holder | 2019-10-12
0 | Generate and review BOM, Gerber files | 2019-10-12
1 | Progress | 50%
v1.1 Complete: Invoice 20191012

## v1.1 20191012
Smartware Computing | INVOICE
| DATE: | 2019-10-12
David Smart 907 Sunrise Blvd | PROJECT: | Telematics Platform
Waterloo, IA 50701 | INVOICE # | 20191012
319-830-6947
Bill To: | Bill Rate $/h | 85
Hughes Fire Equipment, Inc.
c/o Sonny Ovens
910 Shelley Street
Springfield, OR 97477
541-747-0072
DESCRIPTION | HOURS | AMOUNT
Correct v1.0 issues, add RTC battery, update to v1.1 | 1 | 85
| TOTAL | 85
Make all checks payable to Smartware Computing
If you have any questions concerning this invoice, Contact David Smart.
THANK YOU FOR YOUR BUSINESS!